## Slide 1: SharePoint 2013 CU
DEPLOYMENT PLAN

## Slide 2: Agenda
Go Live Plan – hitting the bullseye…
Progress to date and Risks
Resource Alignment & Pre Go Live Preparation
Appendix: Deployment Plan

## Slide 3: Go Live Plan – hitting the bullseye…
4/13 5:00 PM
4/13 10:00 PM
4/14 - 3:00 AM
4/14 - 8:00 AM
4/14 - 1:00 PM
4/14 - 6:00 PM
4/14 - 11:00 PM
4/15 - 4:00 AM
4/15 - 9:00 AM
Backups Completed
4/14 12:00 AM
Production Servers VM image backup – Trib infra team
Farm Backup (full) ::: 4 to 5 hrs.
ContentDB Backup ::: 4 to 5 hrs.
WSPs Backup ::: 1 hr.
14 hive Backup ::: 30 mins.
Suspend Search Service ::: 20 mins.
Fix Missing Features Errors ::: 6 to 8 hrs
Occasional downtime
Prerequisites Completed
4/14 1:00 PM
Break
Install CU ::: 6 hrs – 1 hour per server X 6 servers
Run SharePoint Configuration Wizard ::: 6 hrs – 1 hour per server X 6 servers
Downtime
Cumulative Update (CU) Applied
4/15 2:00 AM
4/15 - 11:00 PM
Break/Contingency
Smoke Test
Verification & Testing
Downtime
(as needed)
CU Applied Successfully
4/15 11:00 PM
Go/No Go Call!
Kick off rollback plan
4/15 9:00 AM
Rollback
System is responsive - major sanity test passed
Entire Farm went down/ major functionality is unresponsive
Infrastructure Team Engagement

## Slide 4: Progress to Date & Risks
Established Test environment (close replica of production)
Applied Cumulative update (CU) on Test
Environment verified by Technical and Business teams
SharePoint Health dashboard showing no security error after the application of CU –Objective achieved.
Resolving Missing Features might take more time. Mitigation/Impact: No impact on end user, it is more sort of cleanup.
Rollback of the entire farm is not tested on the QA environment. Mitigation: Align infrastructure team to capture test environment VM images and restore them.
SharePoint Production environment mayn’t have required resources to hold all the backups taken during Go Live. Mitigation: Chris to work with infrastructure team to make sure at least one of the servers have enough space to store Farm and DB backups.
Progress
Risks/Unknowns

## Slide 5: Resource Alignment & Pre Go Live Preparation
Chris to provide sign off and test evidence before CAB.
Align infrastructure team to be available for backup and roll back (if required).  Chris
Grant required access to Riz’s User ID to run PowerShell scripts and DB admin access on SPSql.  Chris
Confirm availability of enough storage space on Production servers to temporary hold backups  Chris

## Slide 6: Appendix

## Slide 7: Deployment Plan